## Worksheet
Activity	Start	Conclusion
Construction works	2026	June 2029
Award of contract for construction, finishing and installation works – new UL FS building	March 2026	June 2026
Award of contract for construction, finishing and installation works – shared access and external site works	March 2026	June 2026
Award of contracts for furniture, ICT and technological equipment	October 2027	June 2028
Installation of equipment	July 2028	June 2029
Obtaining the occupancy permit	1 April 2029	June 2029
Completion of all project activities	June 2029	March 2030